## Q1 25 26
ICVA Business Plan 2025/26
Quarter 1 - 01/04/25 - 30/06/25
Action | Owner | Measure | Q1 Update
Lead
Immigration Detention Network
Plan immigration detention roundtable event to include wide range of stakeholders | CEO | Venue confirmed, invitee list determined, invites sent out. | Venue booked, invitee list confirmed, invites sent in May, agenda being developed with group.
ICVA supports launch of immigration custody record review pilot | CEO/DM/METM | Support materials produced, training given. | All materials disseminated, training event completed, reviews in progress
QAF 3
Launch QAF 3 to schemes | METM | All support docs are disseminated to schemes, matrices, how to, processes and video etc. | QAF launched on April 1st, 11 schemes going for platinum, good spread across other levels.
Development of National Reporting Tool
Funding bids submitted for reporting tool | DM | Bids submitted where appropriate, feedback taken on board | Two bids submitted and a host of enquiries, unsucessfull as yet, however offer of potential pro bono support towards development of a spec for build
Support
Development of E-Learning Platform
Commission platform | DM | E-Learning platform commissioned, onboarding process complete, staff training planned in. | Complete, training delivered to team and population of the site has begun from the METM.
Consult members on order of population for resources | METM | NEF members given oppurtunity to feed into resources | Consultation undertaken in Q4 NEF and list of priority completed.
Events
ICV online event Volunteers Week 2024 | CEO/METM | Event delivered to give thanks to ICVs, engage/inform upcoming workstreams | Event held in volunteers week over 110 ICVs in attendance, lots of engagement on Op Nova speaker, event a success.
Engagement with Members/ICVs
ICVA will attend regional ICV events in person wherever possible | METM | Member satisfaction survey | SR attended Eastern regional conference held in Norfolk .
Local events will be attended online or by pre-recorded message at member request | CEO/METM | Member satisfaction survey | Event for D and C undertaken, JW has undertaken video for Lancs. and West Mercia
Newsletters
No less than twice per month, usually weekly | DM | Member satisfaction survey | C10 newsletters sent in Q1 including QAF launch, ADHD in Custody resource, NPM Bulletins, Equivalence in Police Custody Healthcare overview, blogs, PFD reports, HMICFRS PEEL Assessment overview, IOPC recommendations, Independent Sentencing Review overview, NPCC interim guidance onsearch of trans detainees following supreme court judgment, Know my Rights website launch, and more. Newsletter continues to be well received by members.
ICV training resources
Focus will be on conversion of existing resources, however, additional briefings can be produced at members’ request | METM | Member satisfaction survey | None requested in reporting period, mock up of use of force training produced, and start made on scheme manager inducion training
NEF
Hold quarterly NEF meetings as a consultative group for ICVA workstreams | METM | Member satisfaction survey | The NEF agreed on priority of training for the new E-Learning platform and were updated on immigration thematic work.
Immigration Network
ICVA will chair and minute bi-annual meetings of an immigration detention network, ensuring the effective cross detention feedback from those held in immigration in police custody | CEO | Member satisfaction survey | 1st meeting of quarter held, pilot overview given, planning session for immigration roundtable held, all actions from previous meeting complete, additional planning meetings added pre roundtable.
TACT Network
ICVA will chair and minute bi-annual meetings of a TACT detention network, ensuring the effective cross detention feedback from those held in TACT detention | CEO | Member satisfaction survey | TACT Network held, planning in progress for TACT event in Q3, good attendance and engagement.
Cuppa and catch up
CEO will run a quarterly informal drop-in session for schemes | CEO | Member satisfaction survey | 1st session held, around 10 scheme managers in attendance, enjoyed the session, confirmed will run more.
Represent
Increase Awareness of ICV role
Re-launch accounts for Instagram, LinkedIn and BlueSky | DM | New content launched, benchmarks for engagement established | Instagram: First month of launch brought in 11 new followers. By the end of Q1 ICVA has received a total of 37 new followers (a 15% increase), with 14 new followers during volunteers week alone. Q1 ICVA receive 3,391 views on posts (34.2% from non-followers) and 224 interactions (e.g. likes). LinkedIn: First month of launch brought in 43 new followers. By the end of Q1 ICVA has received a total of 79 new followers (a 90% increase), with 13 new followers during volunteers week alone. Q1 ICVA received 5,204 impressions, 233 reactions, 25 comments, and 66 reposts.
Volunteers week activities | METM/DM | Content shared across all platforms | Daily content shared on Instagram and LinkedIn with good engagement throughout. Content included: ICV Voices Video, Impact Stats of 24/25 ICV Visits, Thank you Message from Jonathan Hall, Answering Questions about ICV Role.
Publish a blog for public site/sharing | DM | Blog published | 2 blogs published in Q1: Wood Green - A Child First Approach and Volunteers' Week - A Snapshot of a Busy Year
NPM
Chair NPM | CEO | Ongoing | Chair attended monitoring police custody CoE meeting in Strasbourg, ongoing dialogue with HMICFRS regarding OPCAT mandate and PEEL compliance, gave evidence at Covid enquiry roundtable event including info on police custody.
Attendance at annual business meeting | CEO | Attendance/feedback in newsletter for engagement | Chaired annual business meeting/conference in Scotland, good feedback overall, will ensure focus on other detention settings as well as prisons in next event.
NPM updates including task and finish groups, contribution to annual report etc | CEO | Ongoing | Ongoing as needed, including steers given on workstreams around use of force, ministerial engagement and others.
Ensure Stakeholders are aware of issues in custody (HO, MBDIC, NPCC etc)
Produce a stakeholder overview, disseminated via newsletter and directly to HO, NPCC, HMICFRS, IAPDC | CEO | Stakeholders are made aware of reports from ICVA members each quarter. Wider membership is aware of reports from other areas. ICVA raises significant issues as and when necessary. Reforms are made when issues are systemic. | Stakeholder overview for Q4 produced, highlighting issues in staffing, lack of showers and exercise in some places, some issues with wait times for AA's and more.
Review all HMICFRS reports and provide a stakeholder overview, disseminate via newsletter and directly to HO, NPCC, HMICFRS, IAPDIC | METM | Flow of information across monitoring bodies is maintained. ICVA monitors thematic findings of inspection reports for policy positions, member briefings/resources. | There have been no HMICFRS reports in Q1 whilst the inspection framework moves to PEEL. The Met inspection report is expected in Q2 and then a likely hiatus until PEEL reporting begins to include custody in Spring 26
Represent independent custody visiting at PACE Strategy Meetings, Operational Partners Meetings, MBDIC, NPCC Custody Forum | CEO | ICVA ensures that the findings of ICVs are shared at national level. ICVA designs materials for schemes and ICVs that reflect national changes supporting effective monitoring of detention. | CEO attends all Ops Partners meetings, with METM covering where diary clashes occur, acccepted invite to speak at NPCC conference in Q3, and all other stakeholder meetings as requested.

## Q2 25 26
ICVA Business Plan 2025/26
Quarter 2 - 01/07/25 - 30/09/25
Action | Owner | Measure | Q2 Update
Lead
Immigration Detention Network
ICVA to collate and examine data from pilot schemes | DM | Ongoing | 133 Custody Record Reviews received to date, with deadline provided to all schemes for data to be sent by 17.10.25. Early review of the data received to date indicate immigration detainees tend to be held in police custody longer on average than those not detained with an immigration flag, and a particular discrepancy to being held over 24 hours.
QAF 3
Establish QAF Levels with schemes | METM | All schemes are commited to QAF and levels determined | All QAF levels received from schemes, an excellent spread of awards for schemes, METM has provided support to all schemes and queries, Plat assessments underway, being split between METM and CEO for assessments.
Development of National Reporting Tool
Review outcomes of bids, identify further funding pots if necessary, depending on progress of initial bids | DM | Measures to be determined depending on results of fundraising activities | 2 funding bids submitted during Q2, with outcomes expected during Q3. DM continues to seek out funding opportunities suitable to ICVA, with numerous application avenues identified in preparation for ICVA seeking charitable stauts.
Support
Development of E-Learning Platform
Populate platform | METM | Ongoing | 5 modules completed to date.
Design supporting resources for schemes/ICVs | METM | Resources to be produced to include how to add members, assign training and so on. | How to add users guide in train as well as guide on how to get the most out of the e-learning as a scheme manager.
Events
ICV online training event | METM | Member satisfaction survey | Aug 20th - Suicide and Police Custody Session 120 ICVs present, excellent feedback received, session recorded and disseminated to schemes, TACT event booked in for Q3
Set date and book venue for Scheme Managers Conference | OM | Date and venue confirmed, save the date sent. | Agenda complete, bookings opened, e-learning launch, networking session (at scheme request) and lived experience speaker on agenda, bookings progressing well.
Engagement with Members/ICVs
ICVA will attend regional ICV events in person wherever possible | METM | Member satisfaction survey | No regional requests for delivery in Q2, 2 in diary for Q3 for METM and CEO
Local events will be attended online or by pre-recorded message at member request | METM | Member satisfaction survey | Local event in Dorset attended, Hampshire video provided, Warwickshire event attended online.
Newsletters
No less than twice per month, usually weekly | DM | Member satisfaction survey | C12 newsletters sent in Q2 including NPCC Letter Regarding Delays in Access, Confidentiality of Visits, ICVA Stakeholder Overview, IOPC PFDs, Report of the Independent Reviewer of Terrorism Legislation, HMICS Falkirk Inspection, HMICFRS Metropolitan Police Inspection, NPCC Guidance on Searching of Trans Detainees, Northern Ireland Criminal Justice Inspection, Report from APPG on Children in Custody, NPM Bulletins and more. Newsletter continues to be well received by members.
ICV training resources
Focus will be on conversion of existing resources, however, additional briefings can be produced at members’ request | METM | Member satisfaction survey | No requests for materials received in quarter, however letter from NPCC written by ICVA on access to custody shared as a resource for schemes and ICVs.
NEF
Hold quarterly NEF meetings as a consultative group for ICVA workstreams | METM | Member satisfaction survey | The NEF on new and to continuing standing agenda items for future NEFs. NEF agreed to monitor delays and improvements to delays of access through stats return.
Cuppa and catch up
Run an informal drop-in session for schemes | CEO | Member satisfaction survey | Session run in Sept only a handful of schemes, but good engagement on a vareity of topics, childrens concordat etc. Schemes that come seem to value the opp.
Represent
Increase Awareness of ICV role
Publish a blog for public site/sharing | DM | Blog published | Blog on delays to detention published and shared with NPM membership as well as ICVA contacts.
NPM
Chair NPM | CEO | Ongoing | Chair work ongoing, chaired SG and business planning for next year commencing.
NPM updates including task and finish groups, contribution to annual report etc | CEO | Ongoing | Drafts and data for annual report given. Supported population of NPM dashboard and launch.
Ensure Stakeholders are aware of issues in custody (HO, MBDIC, NPCC etc)
Measure ICVA produces a quarterly stakeholder overview, disseminated via newsletter and directly to HO, NPCC, HMICFRS, IAPDC | CEO | Stakeholders are made aware of reports from ICVA members each quarter. Wider membership is aware of reports from other areas. ICVA raises significant issues as and when necessary. Reforms are made when issues are systemic. | Stakeholder overview completed and disseminated for Q1. The main issue raised in Q1 was around delays to access for ICVs, raised with NPCC and letter drafted and disseminated. Will continue to monitor for ongoing issues. Other issues raised included AA's, accessiblity of beds for detainees and a host of maintenance issues.
Review all HMICFRS reports and provide a stakeholder overview, disseminate via newsletter and directly to HO, NPCC, HMICFRS, IAPDIC | METM | Flow of information across monitoring bodies is maintained. ICVA monitors thematic findings of inspection reports for policy positions, member briefings/resources. | Overviews of the HMICFRS report on the MPS completed, also the follow up visit from Northern Ireland to police custody and an inspection from HMICS in Scotland.
Represent independent custody visiting at PACE Strategy Meetings, Operational Partners Meetings, MBDIC, NPCC Custody Forum | CEO | ICVA ensures that the findings of ICVs are shared at national level. ICVA designs materials for schemes and ICVs that reflect national changes supporting effective monitoring of detention. | All Ops partners meetings attended, NPCC Strategic Custody Board, MBDIC, Immigration Enforcement meetings, Also met with HO on new internal concealment offence. Speaking engagements feature NPM prevention materials.

## Q3 25 26
ICVA Business Plan 2025/26
Quarter 3 - 01/10/25 - 31/12/25
Action | Owner | Measure | Q3 Update
Lead
Immigration Detention Network
Collate and examine data from pilot schemes | DM | Data received, analysed and report/overview for roundtable completed | Data from the pilot has been analysed and was presented at the roundtable event. Findings generally indicated that rights and healthcare needs were well met, with some shortcoming identified regarding quality and completeness of custody records, particularly under the Entitlements section where high volumes of no detail entries were noted, as well as concerns regarding immigration specific rights. A significant finding form the pilot was detention time, with data indicating that immigration detainees spend longer on average in police custody than the average detainee.
Hold immigration detention roundtable | CEO | Rountable held, discussions on next steps as part of agenda | Immigration Roundtable held, good attendance overall although no one from APPG, useful discussion held, good feedback from attendees and pilot sites, full overview in team paper.
Consider discussions and next steps arising from roundtable | CEO | to be determined post event | Discussed with Chair and in early Q4 slides and a 'note of the day' will be shared with attendees, report forthcoming from workstream in Q4 and Q1 of following business year.
QAF 3
Ongoing QAF assessments (platinum schemes will be assessed throughout the year) | METM | Ongoing | CEO undertaking platinum assessments for 4 areas, generally progressing well. METM QAF assessments progressing well - one scheme has achieved platinum criteria and all others are on track.
Development of National Reporting Tool
Next steps following outcome of initial bids | DM | Measures to be determined depending on results of fundraising activities | ICVA continues to receive mentorship through the WCIT as part of our previously successful funding bid to receive pro bono support. In addition, ICVA received a successful outcome on a bid to the Evan Cornish Foundation in Q3, with funds of £5,000 to be provided in April 2026 towards costs to commission a series of animated videos towards ICV recruitment.
Support
Development of E-Learning Platform
Launch platform at Scheme Managers Conference | METM | Platform and helpful resources launched, scheme feedback from launch event | E-Learning platform launched, feedback overall on the platform incredibly positive 'game changer' 'amazing' 'fantastic' 'e-learning demo was a standout' some feedback received regarding live set up and differing technical abilities of those present, but overwhelmingly positive feedback overall.
Events
Deliver Scheme Manager Conference | METM | Event completed, feedback received | SM conference delivered with an overall feedback score of 4.69 out of 5 which is excellent. Lived experience speaker, e-learning and adjustments to agenda to reflect PCC announcement most positive feedback. Construcitive feedback focussed on the food and timing of the conference in the Winter.
TACT ICV online training event | CEO | Member satisfaction survey | 63 ICVs and SM's attended the event, held on 23rd Oct online. Agenda included hearing from TACT ICVs, the IRTL/IRSTL and an overview of preventive monitoring. Incredibly positive feedback received on event.
Engagement with Members/ICVs
ICVA will attend regional ICV events in person wherever possible | METM | Member satisfaction survey | CEO attended North West and North Wales regional ICV conference.
Local events will be attended online or by pre-recorded message at member request | METM | Member satisfaction survey | Training for local event in Warwickshire delivered by METM.
Newsletters
No less than twice per month, usually weekly | DM | Member satisfaction survey | C10 newsletter sent in Q3 with topics including Crime Resolution Tracker, New Briefing by ICVA on Using Instagram to Recruit Diverse Volunteers, NPM Bulletins, PFD Reports, Impact of Poor Transport on Court Custody, ICV Recruitment Poster Templates, HMICFRS Reports, Stakeholder Overview, NPCC Policing Charter, Deaths in or Following Custody ICV Briefing, ICV Overview for Custody Staff Resource, Scheme Managers Conference, IOPC Learning the Lessons, E-learning, Use of Force Statistics, Immigration Roundtable, End of Year Blog, NPM Annual Report.
ICV training resources
Focus will be on conversion of existing resources, however, additional briefings can be produced at members’ request | METM | Member satisfaction survey | Modules converted to E-Learning: Induction for ICVs, Induction for TACT ICVs, Induction for SM, Back to Basics, Custody Record Reviewing, Human Rights Overview, and Learning Difficulties and Disabilities
NEF
Hold quarterly NEF meetings as a consultative group for ICVA workstreams | METM | Member satisfaction survey | The NEF discussed vulnerable people, staffing issues, and ensuring schemes are empowered to ensure timely access.
Immigration Network
ICVA will chair and minute bi-annual meetings of an immigration detention network, ensuring the effective cross detention feedback from those held in immigration in police custody | CEO | Member satisfaction survey | Q3 immigration detention network chaired, post roundtable. Good feedback on event received, with news of academic research being undertaken on imm detainees in police custody. Agreement that an additional meeting will be held in Feb as ICVA puts together report and thinks about recommendations arising from work and futher work required such as officers issuing IS91's, on agenda for addtional meeting in Q4.
TACT Network
ICVA will chair and minute bi-annual meetings of a TACT detention network, ensuring the effective cross detention feedback from those held in TACT detention | CEO | Member satisfaction survey | TACT Network meeting held. Discussion on Schedule 3 and 7 had, determined that an additional meeting on this area would be valuable, scheduled for Q4 with background work being undertaken by METM. Ongoing work included in ICVA business plan 26/27.
Cuppa and catch up
CEO will run a quarterly informal drop-in session for schemes | CEO | Member satisfaction survey | Q3 session held, limited attendance but close to Christmas, will review engagement in Q4 and Q1 of following year to determine value.
Represent
Increase Awareness of ICV role
Review social media plan and identify learning to inform rolling plan | DM | Initial 6 month plan reviewed, new plan or strategy considered/produced | Following an initial increase in growth and engagement and a slight plateau toward the end of the 6 month period, an updated strategy has been devised for 2026 with learning reflected and focus on consistent fresh content and trialling new content to support ongoing growth and engagement with updated target audiences.
Publish a blog for public site/sharing | DM | Blog produced | CEO published end of year blog.
NPM
Chair NPM | CEO | Ongoing | Meeting with policing minister undertaken to discuss NPM but also custody visiting. Recruitment of temp Head of NPM Secreteriat, engagement work with IOPC, launch of database and all mandate holders conference attendance.
NPM updates including task and finish groups, contribution to annual report etc | CEO | Ongoing | OPCAT compliance self assessment response drafted with METM, DM attending AI task and finish group.
Ensure Stakeholders are aware of issues in custody (HO, MBDIC, NPCC etc)
Measure ICVA produces a quarterly stakeholder overview, disseminated via newsletter and directly to HO, NPCC, HMICFRS, IAPDC | CEO | Stakeholders are made aware of reports from ICVA members each quarter. Wider membership is aware of reports from other areas. ICVA raises significant issues as and when necessary. Reforms are made when issues are systemic. | Stakeholder overview completed and disseminated for Q2, included improvements in access to suites, improvements for storage of religious materials, issues reported with transport and concerns post panorama programme.
Review all HMICFRS reports and provide a stakeholder overview, disseminate via newsletter and directly to HO, NPCC, HMICFRS, IAPDIC | METM | Flow of information across monitoring bodies is maintained. ICVA monitors thematic findings of inspection reports for policy positions, member briefings/resources. | HMICFRS have had a hiatus in reports whilst they complete first inspections under new framework, reports will be released in Q4. CEO scheduled to attend engagment meeting on thematic findings. In reporting period, overviews given of HMICS report and HMICFRS report on Transport Police custody.
Represent independent custody visiting at PACE Strategy Meetings, Operational Partners Meetings, MBDIC, NPCC Custody Forum | CEO | ICVA ensures that the findings of ICVs are shared at national level. ICVA designs materials for schemes and ICVs that reflect national changes supporting effective monitoring of detention. | NPCC Custody Forum attended and presented at by CEO, METM attended MBDIC, all Ops partners meetings attended. PACE Strat meeting attended. Training session on ICVs and ICVA delivered for Border Force.

## Q4 25 26
ICVA Business Plan 2025/26
Quarter 4 - 01/01/26 - 31/03/26
Action | Owner | Measure | Q4 Update
Lead
Immigration Detention Network
Undertake resultant policy/training activities | CEO | To be determined post roundtable | IDN note of day circulated, Imm E-Learning completed, report drafted and socialised with network.
QAF 3
Complete QAF assessment support/dip sampling | METM | METM (with support from CEO where necessary) to complete all assessments by Q4 end | Assessments and dip sampling either completed or scheduled for first week of Q1 26/27. Excellent engagement from schemes
Development of National Reporting Tool
Next steps following outcome of initial bids | DM | Measures to be determined depending on results of fundraising activities | Spreadsheet mapping questions complete, AI in early days of exploration, funding stalled for time being until charitable status received.
Support
Development of E-Learning Platform
Continue to convert/develop E-Learning resources as requested by schemes | METM | Ongoing - additional conversions to continue until all E-Learning complete. | Physical disabilities completed and launched, Immigration detainees complete and launched, Religious items launched.
Events
ICV online training event | METM | Member satisfaction survey | Largest event to date with over 200 ICVs, expert by experience and mental health theme, excellent feedback.
Engagement with Members/ICVs
ICVA will attend regional ICV events in person wherever possible | METM | Member satisfaction survey | South West and East Mids conferences attended online as online conferences. NW conference attended in person. Agreement to attend N Ireland conference in 26/27.
Local events will be attended online or by pre-recorded message at member request | METM | Member satisfaction survey | METM presented at Sussex ICV Academy online.
Newsletters
No less than twice per month, usually weekly | DM | Member satisfaction survey | 11 newsletters sent during the quarter. Topics included: E-learning update, amends to Mental Health Act, State Threats Legislation, Prevention of Future Deaths Reports, Code of Practice Review, UK NPM Bulletins, ICV Online Event, ICVA's Business Plan, Independent Advisory Panel on Deaths in Custody Chair's End of Year Report, IOPC Youth Panel Manifesto, NPCC Guidance on Suicide Prevention
ICV training resources
Focus will be on conversion of existing resources, however, additional briefings can be produced at members’ request | METM | Member satisfaction survey | Additional Groups created for Scotland on E-Learning so they are better able to manage the different regions. Anti-Racism Training certificate created for schemes to use.
NEF
Hold quarterly NEF meetings as a consultative group for ICVA workstreams | METM | Member satisfaction survey | NEF was updated on ICVA's Code of Practice workstream and consulted on a QAF Awards ceremony.
Cuppa and catch up
Run an informal drop-in session for schemes | CEO | Member satisfaction survey | Drop in session held, better numbers than Q3 and seems to be valued, will continue for new business year and then review.
Represent
Increase Awareness of ICV role
Publish a blog for public site/sharing | DM | Blog published | 3 blogs were published during the last quarter: an anouncement of the Code of Practice review, a blog giving an overview of ICVA's new e-learning platform, and a blog sharing memories of an ICV who died unexpectedly in Lewisham
NPM
Chair NPM | CEO | Ongoing | CEO continues to Chair NPM although has indicated that she will step down this year, will maintain place on SG.
NPM updates including task and finish groups, contribution to annual report etc | CEO | Ongoing | Q4 has seen the recruitment of the new HoS, SG, OPCAT assessment and peer assessment.
Ensure Stakeholders are aware of issues in custody (HO, MBDIC, NPCC etc)
Measure ICVA produces a quarterly stakeholder overview, disseminated via newsletter and directly to HO, NPCC, HMICFRS, IAPDC | CEO | Stakeholders are made aware of reports from ICVA members each quarter. Wider membership is aware of reports from other areas. ICVA raises significant issues as and when necessary. Reforms are made when issues are systemic. | Q3 stakeholder overview produced including issues with staff/healthcare staff attitudes, halal meal certificates and safeguarding issues. Positive reports include increased tech in custody, individualised care and more. Disseminated via newsletter.
Review all HMICFRS reports and provide a stakeholder overview, disseminate via newsletter and directly to HO, NPCC, HMICFRS, IAPDIC | METM | Flow of information across monitoring bodies is maintained. ICVA monitors thematic findings of inspection reports for policy positions, member briefings/resources. | No reports in quarter, however concerns with mission creep of HMICFRS acted upon and esclated ahead of the publication of the first raft of reporting in Q1 of 26/27, receiving a broadly positive response from HMICFRS.
Represent independent custody visiting at PACE Strategy Meetings, Operational Partners Meetings, MBDIC, NPCC Custody Forum | CEO | ICVA ensures that the findings of ICVs are shared at national level. ICVA designs materials for schemes and ICVs that reflect national changes supporting effective monitoring of detention. | PACE Strat, Ops partners and NPCC custody meetings attended, presentation given on immigration work at NPCC custody strat group.